## E27 Test Evidence Matrix
E27 — Acceptance Criteria & Tutoring-Flow Test Evidence Matrix
InClass LLM Platform ¦ Sprint 2 ¦ Date: May 2026
US | Story Title | Acceptance Criteria | Test Input | Expected Result | Actual Result | Status | Evidence | Notes
US-A | Instructor Auth | Valid credentials return successful auth. Unknown email returns clear error. Backend verifies identity before allowing instructor functions. | POST /instructor/login email: bekmezcii@mef.edu.tr password: ilker123 | ok: true, instructor data returned | ok: true, instructor record returned | PASS | Terminal log: 200 OK Instructor dashboard visible | Email+password auth used as equivalent federated auth
US-A | Instructor Auth — Negative | Unknown identity returns clear error. | POST /instructor/login email: unknown@test.com password: wrong | ok: false, error message | ok: false — 'Instructor not found' | PASS | API response verified
US-B | Student Auth | Valid student credentials return successful auth. Unknown student returns clear error. | POST /student/login email: zerdalib@mef.edu.tr password: beyza123 | ok: true, student data returned | ok: true, student record returned | PASS | Terminal log: 200 OK Student dashboard visible
US-C | Role & Course Authorization | Server-side authorization rejects authenticated but unauthorized access. Authorization enforced in backend. | Instructor B (no COMP302 access) tries to list COMP302 activities | ok: false — not authorized | ok: false — 'You are not authorized for this course' | PASS | API response verified | Backend enforces via _check_instructor_ownership()
US-D | List My Courses | Only assigned courses returned. Another instructor's course never visible. | POST /instructor/list-courses beklmezcii@mef.edu.tr (COMP302 owner) | Only COMP302 in results | COMP302 returned, COMP304 not returned | PASS | Response JSON verified
US-E | List Activities | Activity list returned correctly. Each item includes activity number and status. Order deterministic (ascending). | POST /instructor/list-activities course_id: COMP302 | List of activities with activity_no and status | Activities returned with activity_no and status, ordered ascending | PASS | Instructor UI — List Activities button
US-F | Create Activity | Activity created with required fields. Missing fields return clear error. Duplicate activity number rejected. | POST /instructor/create-activity course_id: COMP302, activity_no: 1, text: '...', objectives: [...] | ok: true, activity created | ok: true, activity created in DB | PASS | Supabase activities table — new row visible
US-F | Create Activity — Duplicate | Duplicate activity number in same course rejected. | POST /instructor/create-activity same course_id and activity_no | ok: false — duplicate error | ok: false — 'Activity number already exists' | PASS | API response verified
US-G | Update Activity | Only allowed fields updated. Empty patch rejected. Non-existent activity returns error. | POST /instructor/update-activity course_id: COMP302, activity_no: 1 patch: {activity_text: 'new text'} | ok: true, activity updated | ok: true, text updated in DB | PASS | Supabase activities table — updated row
US-H | Start Activity | Start sets state to ACTIVE. | POST /instructor/start-activity course_id: COMP302, activity_no: 1 | ok: true, status → ACTIVE | ok: true, status changed to ACTIVE | PASS | Supabase activities table — status=ACTIVE
US-H | End Activity | End sets state to ENDED. ENDED activity cannot accept new score logs. | POST /instructor/end-activity course_id: COMP302, activity_no: 1 | ok: true, status → ENDED | ok: true, status changed to ENDED | PASS | Supabase activities table — status=ENDED
US-I | Student — NOT_STARTED Blocked | NOT_STARTED activity is not accessible. | POST /student/get-activity activity with status=NOT_STARTED | ok: false — not started error | ok: false — 'Activity has not started yet' | PASS | API response verified
US-I | Student — ACTIVE + Hidden Objectives | ACTIVE activity returns text WITHOUT exposing learning objectives. | POST /student/get-activity ACTIVE activity | ok: true, activity_text returned, learning_objectives NOT in response | ok: true, activity_text returned, no learning_objectives field | PASS | API response JSON verified — no objectives field | safe_activity object strips objectives
US-I | Student — ENDED Blocked | ENDED activity not accessible. | POST /student/get-activity activity with status=ENDED | ok: false — ended error | ok: false — 'Activity has already ended' | PASS | API response verified
US-I | Non-enrolled Student Blocked | Non-enrolled student access rejected. | POST /student/get-activity yayimlid@mef.edu.tr (not enrolled in COMP302) | ok: false — not enrolled | ok: false — 'Student not enrolled in this course' | PASS | API response verified
US-J | Tutoring Flow — First Message | First response shows activity text and asks exactly one question. | POST /student/chat message: 'start' | Activity text displayed, one question asked | Activity text shown verbatim, one guiding question asked | PASS | Chat UI screenshot — first AI message
US-J | Tutoring Flow — One Question Per Turn | System returns one next guidance question per step. | Multiple student answers submitted sequentially | One question per AI response | AI consistently asks one question at a time | PASS | Chat UI screenshots — sequential messages
US-J | Tutoring Flow — ENDED Activity Stops | If activity is ENDED, flow cannot continue. | Instructor ends activity, student tries to chat | ok: false — activity ended | ok: false — 'Activity has already ended' | PASS | API response verified
US-K | Objective-Based Scoring — First Achievement +1 | First achievement of an objective adds +1 score. | Student correctly answers to trigger objective 1 | score+1, score announced, mini-lesson shown | +1 logged in DB, score announced in chat, mini-lesson displayed | PASS | Supabase scores table — new row Chat UI — green toast +1
US-K | No Repeated Score | Repeating same objective does not add score again. | Same student attempts same objective in same activity again | No new score row, ok: false duplicate | ok: false — 'Score already submitted for this objective' | PASS | Supabase scores table — no duplicate row | Duplicate check per student+course+activity+meta
US-K | Score Logged with Metadata | Every score change logged with student, course, activity, score, metadata. | logScore called with all parameters | Row in scores table with all required fields | Row inserted with student_email, course_id, activity_no, score=1, meta=objective | PASS | Supabase scores table screenshot
US-K | Activity Completion Celebration | When all objectives covered, system celebrates and stops. | Student covers all objectives | Congratulations message, no more questions | AI outputs 'Congratulations! You've mastered this activity.' | PASS | Chat UI screenshot — completion message
US-L | Manual Grading | Instructor can submit manual grade for student in specific activity. Manual grade logged with manual grading event. Unauthorized instructor cannot submit. | POST /instructor/grade-student course_id: COMP302, activity_no: 1, student_email, score | ok: true, score logged with TEACHER_GRADE event | ok: true, row inserted in scores table with manual event | PASS | Supabase scores table — TEACHER_GRADE event row
US-M | Reset Activity | All score records deleted. Activity state set to ENDED. New score logging blocked after reset. | POST /instructor/reset-activity course_id: COMP302, activity_no: 1 | ok: true, scores deleted, status=ENDED | ok: true, all score rows deleted, status=ENDED | PASS | Supabase scores table — rows deleted activities table — status=ENDED
TOTAL: 24 test cases | [5 empty] | 24/24 PASS | All core acceptance criteria verified